## Sheet1
<INSERT TITLE> Search Timeline
Date | Task | Notes/Status updates
Day 1 | Submit the Job Description
1 week later | IHR approves
Week the search kicks off | Search committee complete Diversity.edu
1 week later | Submit Job Posting
1 week later | job posting approved
runs for 2-3 weeks | Search end date
week the ad comes down | Search Committee and TAP go over applications
week the ad comes down | TAP provides scores
week the ad comes down | Create the Master referral
week the ad comes down | Email questionnaire with due date of 1 week later
day after questionnaire due | Search Committee meet
1 week later | Interviews
Day after interviews | Search Committee meet
Next few days after interviews | Final Interview with Elena & Karen
Next day | Recommendations and do write -up
Day after write up complete | Provide an update to SLCL Director
Day after write up complete | Give LAS HR everything
1-3 days after write-up | Get approval for offer
Start Date | Target start date
16 weeks